## Guidance notes
Guidance notes for recruiters:
The template milestone plan is designed to be used as a guide and should be adapted to suit your own organistion's needs.
The plan follows the process by breaking it down into manageable steps which correspond with those outlined in the guide: 'Enrich your Board with the Right Trustees: a guide to trustee recruitment'.
Relevant dates will need to be inserted into cell D4 onwards.
Activities should be edited in column A to reflect the steps you intend to take.
Column B should be used to record any notes, including progress against the activities.
The 'Status' of the activity in column C could include; 'not started', 'active' and 'completed'.
Coloured shading should be used to denote the length of time the activity is planned to take and should help for planning purposes.

## Template Milestone Plan
[Organisation] Trustee Recruitment Plan
Activity | Detail/Notes | Status | Week 1 [date] | Week 2 [date] | Week 3 [date] | Week 4 [date] | Week 5 [date] | Week 6 [date] | Week 7 [date] | Week 8 [date] | Week 9 [date] | Week 10 [date] | Week 11 [date] | Week 12 [date] | Week 13 [date] | Week 14 [date] | Week 15 [date] | Week 16 [date] | Week 17 [date] | Week 18 [date] | Week 19 [date] | Week 20 [date] | Week 21 [date] | Week 22 [date]
STEP 1: PLAN THE PROCESS
Appoint someone to manage the recruitment process. Identify trustees/staff to be involved
Create outline plan and timeline
Check the legal and guidance documents to determine what can/cannot be done | Refer to charity commission for latest guidance www.gov.uk/government/organisations/charity-commission
Determine which recruitment route to take e.g. co-opt on temporary basis, run formal recruitment process appointing in principle pending election by members
STEP 2: IDENTIFY YOUR GAPS & NEEDS
Consider and discuss whether you would like to make a temporary appointment to fill gaps
Consider running trustee's skills assessment
Think about diversity of current board & assess how the board would like to address the issue of diversity and inclusion
Confirm appointment panel, agree dates, venue and timing for advertising, shortlisting and interviews | Provide full list of dates to relevant departments e.g. Marketing & Communications, administrative team
STEP 3: DESCRIBE THE ROLE OF THE TRUSTEE
Draft and finalise trustee role description | Don't forget to include legal requirements
Draft and finalise person specification for trustee | Research DBS requirement
Draft and finalise documentation to be included in application pack including application form, covering letter, restrictions | Involve board Chair in drafting cover letter
Compile application packs for role[s] | Consider Pdf file with separate attachments for editable documents
Write advertisement and/or promotional copy and finalise
Consider running an open session for interested candidates
STEP 4: PROMOTE YOUR VACANCY
Decide on who to target, how to reach them & understand where to promote. Consider using Community First Yorkshire's free online volunteering directory: VINY | https://communityfirstyorkshire.org.uk/what-we-do/volunteering/
Involve Marketing & Communication team for support
Identify a budget, if necessary
Place ad
Inform members recruitment is taking place & invite applicants
Send out application packs and covering letters
STEP 5: SELECT YOUR TRUSTEE
Draft shortlisting criteria for score sheet
Run optional open session for potential candidates
Distribute copies of submitted applications to shortlist/interview panel with scoring matrix
Shortlist
Agree interview questions, exercises or presentation criteria
Notify shortlisted candidates, informing them of any preparations required, and set up interviews
Circulate schedule of interviews | Include contact details for panel should there be any difficulties
Hold interviews and make selection
Notify candidates of outcome | Invite to induction appointment/board meeting
STEP 6: COMPLETE THE FORMALITIES
Take up references
Confirm eligibility by conducting checks
Send letter of appointment, chair's letter & induction invitation
Announce appointment in principle to members
Announce appointment to board
Inform advisors and make changes to relevant documents
Election at next AGM
STEP 7: INDUCT YOUR TRUSTEE
Compile induction pack
Run induction programme
Link in with Community First Yorkshire trustee training and networks | https://communityfirstyorkshire.org.uk/
STEP 8: EVALUATE THE ENTRIE PROCESS
Schedule review/evaluation meetings